## Sheet1
GM2 Gantt Chart
|  | Completion | WEEK 1 - WC 14/05/26 |  |  |  |  | WEEK 2 - WC 21/05/26 |  |  |  |  | WEEK 3 - WC 28/05/26 |  |  |  |  | WEEK 4 - WC 04/06/26
|  |  | Thurs | Fri | Mon | Tues | Wed | Thurs | Fri | Mon | Tues | Wed | Thurs | Fri | Mon | Tues | Wed | Thurs | Fri | Mon | Tues | Wed
1 | General
1.1 | Project Concpetion | Complete | bar: WEEK 1 - WC 14/05/26 Thurs to WEEK 1 - WC 14/05/26 Mon; WEEK 2 - WC 21/05/26 Fri to WEEK 2 - WC 21/05/26 Mon; WEEK 4 - WC 04/06/26 Fri to WEEK 4 - WC 04/06/26 Mon
1.2 | Project Proposal | Complete | bar: WEEK 1 - WC 14/05/26 Mon to WEEK 1 - WC 14/05/26 Wed; WEEK 2 - WC 21/05/26 Fri to WEEK 2 - WC 21/05/26 Mon; WEEK 4 - WC 04/06/26 Fri to WEEK 4 - WC 04/06/26 Mon
1.3 | Risk Assessment | On track | bar: WEEK 1 - WC 14/05/26 Tues to WEEK 1 - WC 14/05/26 Wed; WEEK 2 - WC 21/05/26 Fri to WEEK 2 - WC 21/05/26 Mon; WEEK 4 - WC 04/06/26 Fri to WEEK 4 - WC 04/06/26 Mon
1.4 | Individual Meetings | Not Started | bar: WEEK 2 - WC 21/05/26 Fri to WEEK 2 - WC 21/05/26 Mon; WEEK 3 - WC 28/05/26 Thurs; WEEK 4 - WC 04/06/26 Fri to WEEK 4 - WC 04/06/26 Mon
1.5 | Interim Presentation | Not Started | bar: WEEK 2 - WC 21/05/26 Fri to WEEK 2 - WC 21/05/26 Mon; WEEK 3 - WC 28/05/26 Thurs to WEEK 3 - WC 28/05/26 Mon; WEEK 4 - WC 04/06/26 Fri to WEEK 4 - WC 04/06/26 Mon
1.6 | Project Presentation | Not Started | bar: WEEK 2 - WC 21/05/26 Fri to WEEK 2 - WC 21/05/26 Mon; WEEK 4 - WC 04/06/26 Fri to WEEK 4 - WC 04/06/26 Wed
1.7 | Final Report | Not Started | bar: WEEK 2 - WC 21/05/26 Fri to WEEK 2 - WC 21/05/26 Mon; WEEK 4 - WC 04/06/26 Fri to WEEK 4 - WC 04/06/26 Wed
2 | Experiment
2.1 | Design Rig | Complete | bar: WEEK 2 - WC 21/05/26 Thurs to WEEK 2 - WC 21/05/26 Mon; WEEK 4 - WC 04/06/26 Fri to WEEK 4 - WC 04/06/26 Mon
2.2 | Source Components | Complete | bar: WEEK 2 - WC 21/05/26 Fri to WEEK 2 - WC 21/05/26 Mon; WEEK 4 - WC 04/06/26 Fri to WEEK 4 - WC 04/06/26 Mon
2.3 | Order Components | On track | bar: WEEK 2 - WC 21/05/26 Fri to WEEK 2 - WC 21/05/26 Tues; WEEK 4 - WC 04/06/26 Fri to WEEK 4 - WC 04/06/26 Mon
2.4 | Build Rig | Not Started | bar: WEEK 2 - WC 21/05/26 Fri to WEEK 2 - WC 21/05/26 Mon; WEEK 2 - WC 21/05/26 Wed to WEEK 3 - WC 28/05/26 Fri; WEEK 4 - WC 04/06/26 Fri to WEEK 4 - WC 04/06/26 Mon
2.5 | Run the experiment | Not Started | bar: WEEK 2 - WC 21/05/26 Fri to WEEK 2 - WC 21/05/26 Mon; WEEK 3 - WC 28/05/26 Fri to WEEK 3 - WC 28/05/26 Mon; WEEK 4 - WC 04/06/26 Fri to WEEK 4 - WC 04/06/26 Mon
2.6 | Analyse the Data | Not Started | bar: WEEK 2 - WC 21/05/26 Fri to WEEK 2 - WC 21/05/26 Mon; WEEK 3 - WC 28/05/26 Mon to WEEK 3 - WC 28/05/26 Tues; WEEK 4 - WC 04/06/26 Fri to WEEK 4 - WC 04/06/26 Mon
2.7 | Order any additional parts | Not Started | bar: WEEK 2 - WC 21/05/26 Fri to WEEK 2 - WC 21/05/26 Mon; WEEK 3 - WC 28/05/26 Tues; WEEK 4 - WC 04/06/26 Fri to WEEK 4 - WC 04/06/26 Mon
2.8 | 2nd Round of Experiments | Not Started | bar: WEEK 2 - WC 21/05/26 Fri to WEEK 2 - WC 21/05/26 Mon; WEEK 4 - WC 04/06/26 Thurs to WEEK 4 - WC 04/06/26 Mon
3 | Theory
2.1 | Read Literature to understand the drying problem | Complete | bar: WEEK 1 - WC 14/05/26 Fri to WEEK 2 - WC 21/05/26 Mon; WEEK 4 - WC 04/06/26 Fri to WEEK 4 - WC 04/06/26 Mon
2.2 | Brainstorm possible solutions | Complete | bar: WEEK 1 - WC 14/05/26 Mon to WEEK 2 - WC 21/05/26 Mon; WEEK 4 - WC 04/06/26 Fri to WEEK 4 - WC 04/06/26 Mon
2.3 | Refine solutions as we learn and understand more | On track | bar: WEEK 2 - WC 21/05/26 Fri to WEEK 3 - WC 28/05/26 Mon; WEEK 4 - WC 04/06/26 Fri to WEEK 4 - WC 04/06/26 Mon
4 | Relating back to the product
3.1 | Understand how the experiment relates to Benard's existing product | Not Started | bar: WEEK 2 - WC 21/05/26 Fri to WEEK 2 - WC 21/05/26 Mon; WEEK 3 - WC 28/05/26 Fri to WEEK 3 - WC 28/05/26 Tues; WEEK 4 - WC 04/06/26 Fri to WEEK 4 - WC 04/06/26 Mon
3.2 | Work out how to scale any design solutions to the product | Not Started | bar: WEEK 2 - WC 21/05/26 Fri to WEEK 2 - WC 21/05/26 Mon; WEEK 3 - WC 28/05/26 Tues to WEEK 3 - WC 28/05/26 Wed; WEEK 4 - WC 04/06/26 Fri to WEEK 4 - WC 04/06/26 Mon
3.3 | Offer a cost/benefit analysis on our solution vs other solutions | Not Started | bar: WEEK 2 - WC 21/05/26 Fri to WEEK 2 - WC 21/05/26 Mon; WEEK 3 - WC 28/05/26 Wed to WEEK 4 - WC 04/06/26 Mon
3.4 | Make a recommendation to Benard | Not Started | bar: WEEK 2 - WC 21/05/26 Fri to WEEK 2 - WC 21/05/26 Mon; WEEK 4 - WC 04/06/26 Fri to WEEK 4 - WC 04/06/26 Wed